## Slide 1: Risk Management
SE423: Software Project Management

## Slide 2: Outline
Risk Management Process
Risk Identification
Risk Analysis
Risk Planning
Risk Monitoring
Strategies and Techniques

## Slide 3: Risk Management Process

## Slide 4: What is a Risk?
Problems that haven’t happened yet
Characterized by:
  Uncertainty (0 < probability < 1)
  An associated loss (money, life, reputation, etc)
  Manageable – some action can control it
Needs to be actively identified and managed
  Some choose to ignore – seen as negativity or too much worry
Is a key element in project decision making – especially important for the tough decisions
Proactive vs. Reactive
Active Risk Management is a sign of a well-run project and a mature organization

## Slide 5: What is a Risk?
According to the PMBOK Guide:
  “Project risk is an uncertain event or condition that, if it occurs, has a positive or negative effect on one or more project objectives.”
  “A risk may have one or more causes, and, if it occurs, one or more impacts”
Project Risks
  What can go wrong?
  What is the likelihood?
  What will the damage be?
  What can we do about it?

## Slide 6: Risk Classification
Requirements Risks
  Incorrect
  Incomplete
  Unclear or inconsistent
  Volatile
Cost Risks
  Unreasonable budgets
Schedule Risks
  Schedule compression (customer, marketing, etc.)
Quality Risks
Life Cycle / Operational Risks
Most of the “Classic Mistakes”

## Slide 7: Risk Management Process
Risk management is a systematic approach to reducing the harm due to risks, making a project less vulnerable to challenge or failure and its resulting product more robust
Understanding the hierarchy of Risk Management = Understanding risks and how to deal with them

## Slide 8: Common project, product, and business risks

## Slide 9: Reality check for your project plan
Testing the plan before you begin
Assessing the project using risk management
Involving the team in planning
Building confidence for your plan
Selling the plan to relevant stakeholders

## Slide 10: Risk Identification

## Slide 11: What can Possibly Go Wrong?
Consider the “average” college student:
What risks does the student encounter? How can we mitigate the damage?
  Computer related:
    Lose file;
    Lose flash drive;
    Lose hard drive; damaged
    Lose computer; damaged, lost or stolen
    Crash computer; corrupted files
    No network? Cannot access D2L
  Attendance and time management
    Miss class or late
    Late home work submission
    Miss home work submission

## Slide 12: What can Possibly Go Wrong?
Consider the “average” project:
Testing takes longer than planned – cannot resolve bugs
Vendor cannot deliver a product on schedule
Critical engineer
  Has accident (wipes out in ski jump)
  Becomes a parent
  Has major surgery
Critical engineer leaves project/company
Change of ownership. Project on hold
Major downsizing
Dysfunctional staff
Blizzard and power failures

## Slide 13: Risk Identification: Introduction
Risk identification is concerned with determining what risks might have an impact on the project
In addition, risk identification seeks to profile risks so that effective mitigation and response planning might be possible
Risk identification is an iterative and incremental process that continually adds new risks, deletes non-risks, and refines existing risk profiles as the project progresses

## Slide 14: How to Categorize Risk
Risks: known, unknown, unknowable
Known Risks: Risks that can be uncovered after careful evaluation of the project plan, business and technical environment, and other reliable sources of information (I.e. unrealistic delivery dates, lack of user input, etc.)
  Refer to those risks that can be estimated from historical information
  Can be mitigated by management techniques and through response plans, should they occur
  Example: Potential delay in delivery from third-party vendor
  Example: Key personnel leave project
  Example: Development systems down

## Slide 15: How to Categorize Risk
Predictable Risks [but unknown risks]: Risks that can be extrapolated from past projects. (Staff turnover, poor communication with the customer)
  Refer to those risks that we know have a probability of occurring, but do not know the precise impact
  Cannot be managed directly but can be mitigated by the use of contingency
  Example: Loss of key personnel due to turnover
Unpredictable Risks “Joker” risks that are hard to predict.
Unknowable risks
  Refer to those risks that are outside the scope of historical or probabilistic models for the project
  Are beyond the scope of risk management and usually are addressed by crisis or disaster management
  Examples: Corporate failures, natural disasters, acts of terrorism or war, major snowstorm and power loss

## Slide 16: Risk management model (after Taylor)
Risk Management Planning
Risk Identification
Qualitative Risk Analysis
Quantitative Risk Analysis
Risk Response Planning
Risk Monitoring
Risk Control
Tracking & Auditing (Risk History)
Evaluate & Revise

## Slide 17: Risk Identification
Get the team involved in this process
  Don’t go it alone
Produces a list of risks with potential to disrupt your project’s cost or schedule
Use a checklist or similar source to brainstorm possible risks
Use a SWOT analysis process

## Slide 18: Risk Categories
Types
Classification
Source
Internal / Unique Classifications and Sources

## Slide 19: Where risks are found
Budgets/funding
Schedules
Scope or requirements changes
Project plan
Project management processes
Technical issues
Personnel issues
Hardware
Contracts
Political concerns
Business risk
Legal risk
Environmental risk

## Slide 20: Three Types of Software Risk
Project Risks Threaten the project plan. I.e. if the risks materialize, then it is likely that the project schedule will slip and costs will increase.
  Budgetary/funding
  Schedule
  Personnel issues
  Resources
  Project plan
  Project management processes
  Customers
  Requirements problems – Scope or requirements changes
  Project complexity and size.
  Hardware
  Environmental risk

## Slide 21: Three Types of Software Risk
Technical Risks Threaten the quality and timeliness of the software to be produced.
  Design
  Implementation
  Interfacing
  Verification
  Cutover
  Maintenance
  Security

## Slide 22: Three Types of Software Risk
Business Risks Threaten the viability of the product to be built.
  Building a great product that no-one wants anymore. (Market risk)
  Building a product that no longer fits into the overall business strategy for the company (Strategic risk).
  Building a product that the sales force doesn't understand how to sell.
  Losing the support of senior management due to a change in focus or a change in people. (Management risk).
  Losing budgetary or personnel commitment (Budget risk)
  Contracts
  Political concerns
  Legal risk

## Slide 23: Risk identification: tools and techniques
Documentation reviews
  Effectively, a thorough review of all the inputs to the risk identification process
Information-gathering techniques
  Brainstorming
    With right participants and proper facilitation, brainstorming is a self-regenerating process
  Delphi technique
    Employs a facilitator who distributes a questionnaire to participants and who compiles and synthesizes results
    Participants do not interact directly as they do in brainstorming
Interviews
  Uses standard question and answer techniques with various stakeholders or anyone with project-relevant knowledge

## Slide 24: Risk identification: tools and techniques
Root cause analysis. Technique helps determine the source of risk
  Involves deep analysis of identified risks in order to root out other potential risks
  The source of risk may seem superﬁcial and directly visible: simply, the most immediate source
  However, often the true source of risk—its root cause—is less obvious and not easily detectable
  Hall (1998) suggests using the ‘Five Whys?’ approach
    Ask the question ‘Why?’ ﬁve (more or less) times for each risk
    Each successive question moves closer to the root cause
    Not a highly robust method, but simple and effective

## Slide 25: Risk identification: tools and techniques
Root cause analysis (cont’d)
  Example (based on actual case):
    O-O DB vendor is porting O-O DB to (our) new platform and has been identiﬁed as potential schedule risk
    Why? Vendor has requested additional time to deliver O-O DB
    Why? Vendor did not complete critical intermediate deliverable required for delivery
    Why? Vendor was unable to get concurrency (threads) to work properly
    Why? Vendor is using design from another platform with different OS
    Why? Vendor has no development experience programming with threads
    Note that this is a capability issue, not a technical issue!

## Slide 26: Risk identification: tools and techniques
Checklist analysis
  Based on historical information and previous project team experience – requires one or more similar projects
  Risks can be compiled into a checklist
  Lowest level of the RBS can be used as a starting point for a checklist
  Checklists for projects cannot ever be exhaustive (remember, projects are unique)

## Slide 27: Risk identification: tools and techniques
Assumptions analysis
  Validates the assumptions identified and documented throughout the project planning processes
  Assumptions should be accurate, complete, and consistent
  Assumptions are tested against two factors:
    Strength or validity of the assumption
    Consequences to the project if assumption turns out to be false
  False assumptions should be reclassified as risks
Diagramming techniques
  Cause-and-effect (fishbone or Ishikawa) diagrams
  System or process flowcharts
  Influence diagrams

## Slide 28: Cause and Effect Diagram
Also known as the Ishikawa (or fishbone) diagram
Show the relationship between the effects of problems and their causes
Depicts every potential cause and sub-cause of a problem and the effect that each proposed solution will have on the problem
Useful as a tool for visually representing and capturing cause-and-effect relationships

## Slide 29: Fishbone Diagram

## Slide 30: Cause-and-effect diagram

## Slide 31: System or process flowcharts
Familiar diagram to most stakeholders
Shows logical steps needed to accomplish an objective
Shows how elements of a process or system relate to each other
Depicts cause/response relationships
Document
results
Risk response plan executed?
Response plan reviewed for effectiveness
Risk owner notifies PM of event or risk trigger
Review risk scores
High risk score?
Assign resources/
implement response plan
Monitor response plan execution
Review risk and risk response plan
Y
Y
N
N
Preparation
symbol
Decision
symbol
Process
symbol
Termination
symbol

## Slide 32: Influence diagrams
Primarily used to show the causal influences among project variables
May also show the sequencing of events
Used to visually depict risks (or decisions), uncertainties or impacts, and how they influence each other
Quality
Cost
Scope
Time

## Slide 33: Risk Identification Techniques
Identification based on past experience.
Identification based on historical data, perhaps through the use of a project database.
Decision Driver Analysis, where the key decisions are examined for risk. The factors influencing decisions offer possible sources of risk.
Threat identification in security risks

## Slide 34: Risk Item Checklist
A checklist is useful for supporting risk identification of known and predictable risks in the following subcategories:
Product size – risks associated with the overall size of the software to be built or modified.
Business impact – risks associated with constraints imposed by management or the marketplace.
Customer characteristics – risks associated with the sophistication of the customer and the developer's ability to communicate with the customer in a timely manner.
Process definition – risks associated with the degree to which the software process has been defined and is followed by the development organization.
Development environment – risks associated with the availability and quality of the tools to be used to build the product.
Technology to be built – risks associated with the complexity of the system to be built and the "newness" of the technology that is packaged by the system.
Staff size and experience – risks associated with the overall technical and project experience of the software engineers who will do the work.

## Slide 35: Product Size Risks
Project risk is directly proportional to product size.
Measure the following sizes against previous projects. If those projects were successful & results are similar, then risk is probably low. If a large negative deviation is observed then risk is HIGH.
  Estimated size of the product in LOC or FP?
  Degree of confidence in estimated size estimate?
  Estimated size of product in number of programs, files, transactions?
  Percentage deviation in size of product from average for previous products?
  Number of users of the product?
    Impact on system (loading)
  Anticipated volatility of the requirements?
  Amount of reused software?

## Slide 36: Business Impact Risks
The following items help identify generic risks associated with business impact:
  Effect of product on company revenue.
  Visibility to senior management.
  Reasonableness of delivery deadline
  Number of customers who will use the product & consistency of their needs.
  Number of other products that it will interact with.
  Sophistication of end users.
  Governmental constraints.
  Costs associated with late delivery or a defective product?

## Slide 37: Customer Related Risks
The following items help identify generic risks associated with the customer:
  Have you worked with the customer in the past?
  Does the customer have a solid idea of what is required?
  Is the customer willing to commit significant time to the requirements gathering process?
  Is the customer willing to establish rapid communication links with the developer?
  Is the customer willing to participate in reviews?
  Is the customer technically sophisticated in the product area?
  Does the customer understand the software process?
Risks should be investigated if the answer to any of these questions is “NO”.

## Slide 38: Process Risks
An ill defined software process and/or an ad hoc approach to analysis, design, and testing can introduce risk.
The following are sample questions that should be asked to identify process risk:
  Do you have a consistent repeatable process that is actually used?
  Do you train all developers in the process?
  Are formal technical reviews part of this process?
  Do you have a mechanism for managing change? (i.e. formal RFC system + configuration management).
  Do you have specific methods that you use for each phase of the process?
  Is the process supported by tools?
  Do you manage the process through use of metrics?
Risks should be investigated if the answer to any of these questions is “NO”.

## Slide 39: Technology Risks
Pushing the limits of technology is challenging & exciting, yet very risky.
Questions to identify risk include:
  Is the technology to be built new to your organization?
  Do the requirements require the creation of new algorithms?
  Does the software interface with new or unproven hardware or unproven vendor products?
  Do the requirements require the creation of components that are unlike anything your organization has previously built?
  Do requirements demand the use of new analysis, design, or testing methods?
  Do requirements put excessive performance constraints on the product?
Risks should be investigated if the answer to any of these questions is “YES”.

## Slide 40: Development Risks
The software engineering environment supports the project team, the process, and the product.
If the environment is flawed, it can be a source of significant risk:
  Is a software project management tool available?
  Are tools for analysis and design available?
  Are compilers and code generators available and suitable for the product to be built?
  Are testing tools available and suitable?
  Are the software tools integrated with each other?
  Are team members trained in the use of the tools?
  Are tool mentors available?
Risks should be investigated if the answer to any of these questions is “NO”.

## Slide 41: Staff Size and Experience Risks
CEOs have frequently observed that “people” make the most significant difference to the success of the organization.
  Are the best people available?
  Do the people have the right combinations of skills?
  Are enough people available?
  Are staff committed for the duration of the product?
  Are some people working on multiple projects?
  Have staff received necessary training?

## Slide 42: Risk Components and Drivers
The US Air Force requires project managers to identify
risk drivers that affect software risk components.
Performance risk – the degree of uncertainty that the product will meet its requirements and be fit for its intended use.
Cost risk – the degree of uncertainty that the project budget will be maintained.
Support risk – the degree of uncertainty that the software will be easy to correct, adapt, and enhance.
Schedule risk – the degree of uncertainty that the project schedule will be maintained and that the product will be delivered on time.

## Slide 43: Output: Risk Register
The output of the Risk Identification process is the risk register
All information gathered and generated during the Risk Identification process is documented in the risk register
Risk register contains the following elements [and more]:
  List of identified risks
  List of potential responses
  Root causes of risks
  Updated risk categories
  Probability
  Impact
  Triggers

## Slide 44: Risk Analysis

## Slide 45: Risk Analysis
Numerical analysis of risk allows:
  Make response decisions
  Determine overall project risk
  Add probability to predictions
  Prioritize risks
  Factor risk into cost, schedule, or scope targets
Calculating Risk Exposure

## Slide 46: Risk Analysis
Risk Exposure Examples
  “Facilities not ready on time”
    Probability is 25%, size is 4 weeks, RE is 1 week
  “Inadequate design – redesign required”
    Probability is 15%, size is 10 weeks, RE is 1.5 weeks
How to Estimate
  Impact: The size of the loss – break into chunks
  Probability:
    Use team member estimates and have a risk-estimate review
    Use Delphi or group-consensus techniques
    Use gambling analogy” “how much would you bet”
    Use “adjective calibration”: highly likely, probably, improbable, unlikely, highly unlikely
Sum all RE’s to get expected overrun

## Slide 47: How risk averse are you?
Risk averse people:
  I like being dependable and I’m usually punctual.
  I am not likely to take chances.
  I am responsible and prefer to work efficiently.
  I am more service oriented than self oriented.
  I value institutions and observe traditions
Risk seeking people:
  I like action, and I act impulsively at times.
  I seek excitement for the thrill of the experience.
  I am resourceful and prefer not to plan or prepare.
  I am more self oriented than service oriented.
  I like to anticipate another person’s position.
Risk neutral people:
  I trust my intuition, and I am comfortable with unknown.
  I think about the future and have long-range objectives.
  I am naturally curious and often ask, “Why?”
  I enjoy generating new ideas.
  I work best when I am inspired.

## Slide 48: Elements of Risk Analysis
What are the risks involved in getting to work?
Reduce the occurrence and/or impact of the risk.
Identify new risks as they occur & report on all known risks.

## Slide 49: Risk Management
Risk assessment
Objectives
Analyze risk in a cost-efficient manner
Determine source of risk
Determine risk exposure
Determine time frame for action
Determine highest-severity risks

## Slide 50: Assessing Project Risk
Have top software and customer managers formally committed to support the project?
Are end-users enthusiastically committed to the project and the system/product to be built?
Are requirements fully understood by the software engineering team and their customers?
Have customers been involved fully in the definition of requirements?
Do end-users have realistic expectations?
Is project scope stable?
Are project requirements stable?
Does the software engineering team have the right mix of skills?
Does the project team have experience with the technology to be implemented?
Is the number of people on the project team adequate to do the job?
Do all customer/user constituencies agree on the importance of the project and on the requirements for the system/product to be built?

## Slide 51: Risk Management
Reactive Risk Management
project team reacts to risks when they occur
mitigation – plan for additional resources in anticipation of fire fighting
fix on failure – resources are found and applied when the risk strikes
crisis management – failure does not respond to applied resources and project is in jeopardy
Proactive Risk Management
formal risk analysis is performed
organization corrects the root causes of risk
  TQM concepts and statistical SQA
  examining risk sources that lie beyond the bounds of the software
  developing the skill to manage change

## Slide 52: Proactive Risk Strategies
Begins long before technical work is initiated.
Potential risks are identified.
Probability and impact of risks are assessed.
Risks prioritized by importance.
Software team establishes a plan to manage the risk.

## Slide 53: Inputs to qualitative risk analysis
Organizational process assets
  Historical information from previous projects
  Includes formal or informal ‘lessons learned’ as well as closure documentation and/or post mortems
Project scope statement
  Identifies initially-defined risks
Risk management plan
  Provides framework within which to perform risk analysis
Risk register
  Provides a comprehensive enumeration and description of all project risks

## Slide 54: Risk Analysis
Determine impact of each risk
Risk Exposure (RE)
  a.k.a. “Risk Impact”
  RE = Probability of loss * size of loss
  Ex: risk is “Facilities not ready on time”
    Probability is 25%, size is 4 weeks, RE is 1 week
  Ex: risk is “Inadequate design – redesign required”
    Probability is 15%, size is 10 weeks, RE is 1.5 weeks
  Statistically are “expected values”
  Sum all RE’s to get expected overrun
    Which is pre risk management

## Slide 55: Risk Analysis
Estimating size of loss (impact)
  Loss is easier to see than probability
    You can break this down into “chunks” (like WBS)
Estimating probability of loss
  Use team member estimates and have a risk-estimate review
  Use Delphi or group-consensus techniques
  Use gambling analogy “how much would you bet”
  Use “adjective calibration”: highly likely, probably, improbable, unlikely, highly unlikely
Risk Prioritization
  Remember the 80-20 rule
  Often want larger-loss risks higher – Or higher probability items
  Possibly group ‘related risks’
  Helps identify which risks to ignore – Those at the bottom

## Slide 56: Risk probability and impact assessment
First, assess the probability that the identified risk will occur
Second, determine the impacts of the risk on project objectives: time, scope, quality, and cost
Assessment helps determine which risks require aggressive management
Probabilities and impacts are defined in the risk management plan under the heading definitions of risk probability and impact

## Slide 57: Probability and impact matrix
Defines a combination of risk probability and risk impact that helps determine which risks need detailed risk response plans
  Example: A risk with a high probability of occurring and a high impact will be a strong candidate for a risk response plan
Matrix is typically defined by the organization
If organization does not define a matrix, develop one during planning meetings and analysis
We will look at the probability and impact matrix in the Qualitative Risk Analysis process, where it is used

## Slide 58: Probability
Probability is the likelihood that an event will occur
  Fair coin flip: 0.5 probability of getting heads, 0.5 probability of getting tails
  Sum of probabilities of all outcomes adds up to 1.0
  For any event e, the probability p that e will occur is 0.0 ≤ pe ≤ 1.0
  The complementary probability that e will not occur is just 1.0 - pe
Risk probability is the probability that the risk event will occur sometime during the life of the project and is most often determined through expert judgment
Ways to improve the utility of risk probabilities
  Develop consistent decision criteria for determining probabilities
  Involve as many experts as you can

## Slide 59: Quantifying risk probability
For most situations, use of a ﬁve-point Likert scale is appropriate:
  Highly unlikely (p < 20%)
  Unlikely (20% < p < 40%)
  About even (40% < p < 60%)
  Likely (60% < p < 80%)
  Highly likely (p > 80%)
For less well-deﬁned situations, use a three-point scale:
  High (p > 75%)
  Moderate (35% < p < 75%)
  Low (p < 35%)

## Slide 60: Impact
Impact is the amount of pain or gain the risk event poses to the various project objectives: cost, time, scope, and quality
  Like probability, risk impact may be characterized on a subjective scale (low, medium, high)
  Like probability, a cardinal (numeric) scale of impact is needed for the probability and impact matrix
Employ consistent decision criteria when using a subjective scale
  Establish a consistent means of determining what moves a borderline impact into one impact category or another

## Slide 61: Risk Prioritization
Remember the 80-20 rule
Often want larger-loss risks higher
  Or higher probability items
Possibly group ‘related risks’
Helps identify which risks to Ignore
  Those at the bottom
Use Risk Register

## Slide 62: Risk Prioritization
How to prioritize risks?
One way to prioritize risks is to estimate the probability of its occurrence and its consequences (loss) when it does occur.
The expected value of the loss for the risk can be used for prioritization. This expected value is called risk exposure. If Pr is the probability of a risk R occurring and Lr is the total loss incurred if the risk materializes, then risk exposure RE, for the risk is given by the following equation:
      REr = Pr X Lr

## Slide 63: Assessing probability and impact
Probability and impact values are defined in order to readily place a value on a risk event
Use predefined probability and impact values as a starting point for a project and customize them as needed for the organization
Use brainstorming or the Delphi technique to establish or refine the probability and impact values
During Qualitative Risk Analysis process, determine and assess probability and impact for every risk identified during the Risk Identification process
Document probability and impact and any assumptions used to arrive at these values

## Slide 64: Probability and impact matrix
Risk probability and impact values are nice, but what we need is a single value to characterize the combined effects of these two risk influences: the risk rating
This is what a probability and impact matrix does: it assigns an overall risk rating to each risk
The combination of probability and impact results in an ordinal (order-based) risk rating usually expressed as low, medium, or high
A risk with high probability and high impact (and hence, high risk rating) warrants further analysis and a formal response plan in the Risk Response Planning process

## Slide 65: Probability and Impact Matrix
Notes: Each risk is rated on its probability of occurring and impact if it does occur. The organization’s thresholds for low (dark gray), moderate (light gray) or high (black) risk as shown in the matrix determines the risk’s score.
PMBOK Guide, 4th Edition, p. 137.

## Slide 66: Risk data quality assessment
Low-quality data renders qualitative risk analysis almost useless
Quality assessment examines:
  Quality of data used
  Availability of data for identified risks
  How well the risk is understood
  Reliability and integrity of data
  Accuracy of data
Risk categorizations
  Entries in the RBS can help identify the project phase and determine the elements of the project that are affected by risk

## Slide 67: Risk urgency assessment
Do not try to deal with all risks at the same time
Analogous to rolling wave planning: determine how soon potential risks might occur
Develop risk response plan for those risks that might occur soon
For greater efficiency and effectiveness, only the top ten risks should be actively managed
Maintain a watch list of the remaining risks to replace those on the 'top 10’ list that are mitigated, controlled, eliminated, or that don't materialize

## Slide 68: Outputs: Updates to the risk register
Update risk register with the following information:
  Risk ranking of identified risks. Order the identified risks by risk rating
  Risks grouped by categories. Identify low, medium, and high risk groups to allow easier risk urgency assessment and planning
  List of risks requiring near-term responses
  List of risks for additional analysis and response
  Watch list of low-priority risks. Low-priority risks can still impact a project – monitor them
  Qualitative Risk Analysis trends. Look for patterns that might help in response planning

## Slide 69: Risk Planning

## Slide 70: Introduction
Risk Management Planning addresses how to approach, plan, and execute all of the project risk management activities
The risk management plan is critical to the overall risk management process
  Risk management plan is an input to every other risk-related process in the Planning Process Group
  A well-defined, comprehensive risk management plan enhances the chances of success of the risk management process

## Slide 71: Risk Management Planning
Risk analysis and planning should continue throughout the project
Risks can be eliminated, but impact analysis should be completed first
Develop risk response strategies

## Slide 72: Risk Resolution
Risk Avoidance
  Don’t do the project at all
  Scrub from system
  Off-load to another party
Problem control
  Develop contingency plans
  Allocate extra test resources
Knowledge Acquisition
  Investigate/ research
  Buy information or expertise about it
Risk Transfer
  To another part of the project (or team)
  Move off the critical path

## Slide 73: Input to risk management planning
Enterprise environmental factors
  Concerned with aspects of the enterprise outside of project
  One source may be enterprise historical information
  Industry or academic research is another excellent source
    Example: The Gartner Reports
    comp.risks (Usenet discussion group/mailing list, see reading list)

## Slide 74: Input to risk management planning
Enterprise environmental factors
  Most critical environmental factors are the risk tolerance levels of the organization and the stakeholders
    Risk tolerance expresses an inherent trade-off decision between benefits and cost
    Stakeholders will take a risk if the benefits to be gained outweigh what could be lost
    Conversely, stakeholder will avoid taking a risk because the cost or impact is too great for the amount of benefit that can be derived

## Slide 75: Input to risk management planning
Organizational process assets
  Organization may already have policies and guidelines that define its risk tolerance
Project scope statement
  Project assumptions, constraints, and initial defined risks in scope statement
  The project scope statement contains several information sources for risk management planning:
    Project deliverables
    Project constraints
    Project assumptions
    Initial project organization
    Initial defined risks
    Schedule milestones

## Slide 76: Input to risk management planning
Risk management plan
  Risk categories (e.g. as defined in RBS) are primary source of input
  Budget and schedule for risk management activities
Project management plan
  Project management plan contains schedule, budget, and quality plans which may be sources of risks
  Risk management plan becomes an integral part of the project management plan
  All other project management processes and guidelines comprising the project management plan should be considered in light of potential risks
  Risk management plan should be consistent with the overall direction and management approach of the project

## Slide 77: Risk management planning: tools & output
Risk management planning tools
  Planning meetings are the main tool for risk management planning
  Attendees should include the project manager, members of the project management team, and stakeholders who can contribute risk-related information
  Meetings will involve analysis of risk for the project, risk tolerance of the organization, and calibrating risk to the project and organization
Risk management planning output
  The risk management plan is the only output from the risk management planning process
  Risk management plan is detailed on following slides

## Slide 78: Risk management plan content
Methodology. How risk management will be performed, including methods, tools, and sources of data
Roles and responsibilities. Team of people responsible for managing identified risks and responses, the risk ‘owners’
Budgeting. Assign resources and estimate costs of risk management and its methods
Timing. Timing and frequency of the risk management processes
Risk categories. Develop and review during planning. Used in risk identification

## Slide 79: Risk management plan content
Definitions of risk probability and impact. Discussed in detail in Qualitative Risk Analysis
Probability and impact matrix. Discussed in detail in Qualitative Risk Analysis
Revised stakeholder tolerances. Risk planning may result in changes in stakeholder tolerance
Reporting formats. Describes the content and format of the risk register, the dictionary of risks for project
Tracking. Describes how the risk activity history will be documented and how risk processes will be audited

## Slide 80: Risk categories
Risk categories are identified during risk management planning
Risk categories systematically classify risks and provide a context for understanding those risks
Used in successor process, Risk Identification
Starting point list of risk categories:
  Technical, quality, or performance risks
  Project management risks
  Organizational risks
  External risks

## Slide 81: Risk categories
Technical/quality/performance risks
  Unproven or complex technology
  Changes to technology anticipated during the course of the project
  Unrealistic quality goals
  Unrealistic performance goals
Project management risks
  Improper schedule and resource planning
  Poor project planning
  Improper or poor project management disciplines or methodologies

## Slide 82: Risk categories
Organizational risks
  Resource conflicts due to multiple projects occurring at the same time in the organization
  Unrealistic scope, time, and cost objectives with respect to the organization’s resources or structure
  Lack of funding for the project or diversion of funds from the project to other projects
  Management oversight changes
  Loss of project ‘champion’
  Project ‘politics’

## Slide 83: Risk categories
External risks
  New laws or regulations
    Example: Sarbanes-Oxley Act of 2002 (corporate governance and financial practice) – “Compliance should be planned and implemented as a normal project”
  Labor issues
  Weather
  Changes in ownership
  Changes in foreign policy for projects performed (all or in part) in other countries
  Catastrophic risks (force majeure) are outside the scope of risk management planning – require disaster recovery techniques
    Examples: Earthquakes, meteorites, volcanoes, hurricanes, floods, civil unrest, terrorism, etc.

## Slide 84: Risk Breakdown Structure (RBS)
Risk categories can be represented visually in a Risk Breakdown Structure (RBS) diagram
Provides hierarchical decomposition of risk categories
Analogous to WBS
Project
Technical
Project Management
Organizational
External
Unproven Technology
Quality
Performance
Complex Technology
Schedule Planning
Project Disciplines
Resource Planning
Cost Estimates
Budgets
Project Schedules
Unrealistic Objectives
Lack of Funding
Weather
Labor Issues
Catastrophic Risk
Technology Changes
Management
Laws & Regulations

## Slide 85: Risk Response Planning: Introduction
Risk response planning is concerned with developing options and possible reactions to mitigate threats and exploit opportunities discovered during the risk analysis processes
The severity of the risk dictates the level of risk response planning that should be performed
A risk with low severity is not worth the time it takes to develop a detailed risk response plan
Risk responses should be cost effective
  If the response cost is more than the cost of the risk, formulate a less-costly risk response

## Slide 86: Risk Response Planning: Introduction
Risk responses must be timely
  An untimely risk response itself becomes a risk
Risk responses must be agreed to by all the project stakeholders
Risk responses must be assigned to an individual (the risk owner) who is responsible for monitoring the risk and executing the risk response plan if needed

## Slide 87: Risk Monitoring

## Slide 88: Risk Monitoring
Top 10 Risk List
  Rank
  Previous Rank
  Weeks on List
  Risk Name
  Risk Resolution Status
A low-overhead best practice
Interim project post-mortems
  After various major milestones
Communicate w/ Stakeholders!

## Slide 89: Monitor and Control Risks
Concepts
  Workarounds – unplanned corrective action for unanticipated problems
  Risk Reassessments – periodic risk review and adjustments
  Risk Audits – proves risk preparedness and provides lessons learned
  Reserve Analysis – accounting for risk reserves (financial and schedule), which are only for risk
  Status Meetings – should primarily focus on risks
  Closing Risks – the conditions surrounding a risk are in the past, and the risk should be closed
Outputs: Risk Register Updates, Change Requests, PM Plan Updates, Project Document Updates, Lessons Learned

## Slide 90: Miniature Milestones
Use of small goals within project schedule (1-2 days)
Reduces risk of undetected project slippage
Requires a detailed schedule, including early milestones
Use binary milestones (done or not done)
Pros
  Enhances status visibility
  Good for project recovery
  Can improve motivation through achievements
  Encourages iterative development
Cons
  Increase project tracking effort

## Slide 91: Basic principles
Risks must be managed
Risk must always be one of the principle concerns of the project management team
Risks must be reported
  Risks should be an agenda item in weekly team meetings
  Risks should be included in the project status report
  Weekly project review should review all risks
Team meeting
  Should briefly review all outstanding risks
  Should estimate whether each risk’s probability has increased, has decreased, or is unchanged
  Risk owners should report on their assigned risks

## Slide 92: Basic principles
In the project status report, list all risks for which the degree of risk has changed
Weekly project review
  Review all risks, even those that have been eliminated
  Goal is to uncover new risks or identify those that have been reincarnated
Reviewing risks in weekly team meetings keeps the team and risk owners aware and sensitized to risks
Including risks in the project status report prepares management for the time(s) when risks happen

## Slide 93: Seven Principles
Maintain a global perspective
Take a forward-looking view
Encourage open communication
Integrate
Emphasize a continuous process
Develop a shared product vision
Encourage teamwork

## Slide 94: Risk Management Conclusion
Avoid Common Errors
Risk Management should be the focus of Status Meeting
Risk Management is often not used in Project Management, but has high ROI
Risks are both good and bad
Funds/time set aside for risks are necessary
Communicate

## Slide 95: Strategies and Techniques

## Slide 96: Strategies for negative risks or threats
Avoidance
  Risk avoidance evades a risk, eliminates the cause of the risk event, or changes the project plan to protect the project objectives from the risk event
  Risk avoidance eradicates the risk by removing the risk or its cause
  Risk avoidance is most suitable in the early stages of a project, through improved communications, additional resources, or more-clearly defined scope
  Example: Risk of interfacing Membership Management System (MMS) to external art museum membership systems can be avoided by eliminating requirement to do so

## Slide 97: Strategies for negative risks or threats
Risk transfer
  Risk transfer moves the risk and the consequences of that risk to a third party
  Responsibility for the management of that risk now rests with another party
  Risk transfer comes in many forms but is most effective for financial risks
    Example: Insurance is one form of risk transfer

## Slide 98: Strategies for negative risks or threats
Contracting
  Contracting is another form of risk transfer
  The contractor accepts certain aspects of the risk and responsibility for the cost of failure
  Types of contracts:
    Fixed-price contract. Contractor increases cost of the contract to compensate for the level of risk they are accepting
    Cost reimbursable contract. Contractor receives compensation for additional costs. Majority of the risk remains with the buyer [remember the VCF]

## Slide 99: Risk Mitigation, Monitoring, and Management
Mitigation – how can we avoid the risk?
Monitoring – what factors can we track that will enable us to determine if the risk is becoming more or less likely?
Management – what contingency plans do we have if the risk becomes a reality?

## Slide 100: Strategies for negative risks or threats
Mitigation
  Risk mitigation attempts to reduce the probability of a risk event and/or its impacts to an acceptable level
  Risk mitigation takes the viewpoint that fixing a problem earlier in a project is less costly than fixing it later
  Examples: Performing more tests, using simpler processes, perform simulations, choose vendors for reliability over cost
Risk acceptance
  The risk is acknowledged, but no action is taken unless the risk occurs
  Appropriate when it is not possible or cost-effective to address a speciﬁc risk in any other way
  Passive acceptance simply documents that the acceptance strategy has been adopted and leaves the project team to deal with the risks
  Active acceptance establishes risk reserves, such as a pool of funds, time, or resources to be held for use in response to a risk event

## Slide 101: Strategies for negative risks or threats
Risk contingency plans
  Contingency planning involves planning alternatives to deal with the risks should they occur
  Contingency plans do not seek to reduce the probability or impact of risks—the strategy accepts that the risk may occur and plans ways to respond to the risk
  A contingency plan is executed when the risk event occurs
  Contingency plans must be in place well before the time the risk may occur
  Contingency (fallback) plans are developed for risks:
    With very high impact or:
    With response strategies that may themselves be risky
  Contingency plans usually entail a signiﬁcant alternative path through part of the project
  Example: disaster recovery plan

## Slide 102: Contingency planning tools
Contingency allowances (or reserves). Contingency allowances provide a pool of funds, time, or resources that are held for use in response to an unavoidable risk event
  Example: Including contingency time in case of loss of key personnel
Fallback plans. Fallback (or ‘Plan B’) plans are developed for risks with high impact or for risks with strategies that may in themselves be risky
  Fallback plans may be used to address secondary risks
  Example: Use of a relational database plus object-oriented interface in place of pure O-O database

## Slide 103: Strategies for positive risks or opportunities
Exploitation
  Exploitation involves looking for opportunities for positive impacts
  Example: Reduce project duration by using more experienced resources on critical tasks
Sharing
  Sharing is the positive analog to transferring
  Sharing assigns risk to a third-party owner who is better able to use the opportunity the risk presents
  Example: Form a joint venture between a technical software company and marketing and sales firm

## Slide 104: Sidebar: Residual and secondary risks
Secondary risks arise as a result of implementing a risk response – they are the risks inherent in the response
  Identify and plan responses for secondary risks using tools such as fallback plans
  Example: O-O/RDB expert consultant becomes ill
Residual risks are those that cannot be effectively dealt with within the rest of the risk plan
  Example: Some risk may remain as a result of other response plans. Residual risks are usually dealt with through contingency reserves
  Example: Developer skills risks (resource planning risk) associated with alternate database solution

## Slide 105: Risk response planning outputs
Risk register updates
List of identified risks, including:
  Descriptions
  WBS element or area of the project impacted
  Categories (RBS)
  Root causes
  Project objectives impacted by the risk impacts
  Risk owners and their responsibilities
  Risk triggers – precursors to risk event; Trigger conditions, symptoms, and warning signs of a risk occurrence
Response plans and strategies
  Speciﬁc actions to implement the chosen response strategy
  Fallback plans if the primary response strategy proves inadequate

## Slide 106: Risk response planning outputs
Risk register updates
Cost and schedule activities needed to implement risk responses
Contingency plans
  Contingency plans and triggers for their execution
  Contingency reserves for cost, time, and resources
  Fallback plans
List of residual and secondary risks
Probabilistic analysis of the project and other outputs of the qualitative (and quantitative) risk analysis processes